## Antibody
|  | In house |  | 3 Months |  | 2 Months | [9 empty] | 3 Months | [11 empty] | 2 Months | [5 empty] | 2 Months | 2 Months | 2 Months
Oursource
抗體標的 | 細胞株編號 | 委外代工 | 狀態 | 免疫注射 | 融合篩選 | 親和力測試 | 細胞擴增 | 抗體純化 | 全抗原親和力測試 | 抗原種類 | 抗原決定位確認 | 抗原決定位 | 結構穩定性測試 | 極限測試 | 交叉反應 | CDR 基因定序 | CDR定位/解序 | 抗體分型 | 輕鏈 | 基因轉殖 | 抗體表現 | 胺基檢測 | 芳香族檢測 | 還原態蛋白 | 非還原態蛋白 | 內毒素 | 生產量 | 結構穩定性測試 | 功能性驗證 |  |  |  |  | 親和力測試 | 產品生產 | 品質文件 |  | 上架 | 銷售
Monoclonal Ab | Clone No. | Oursource | Status | Immunization | Fusion/Selection | Affinity testing | Cell propagation | Ab purification | Antigen response | Antigens | Epitope mapping | Epitope region | Structure Stability | Limit of Detection | Cross-reactivity | CDR Sequencing | CDR mapping | Subtype of IgG | light chain | Vectoe Cloning | Ab expression | HPLC-SEC-214 | HPLC-SEC-280 | SDS-PAGE (Reduced) | SDS-PAGE (Non-R) | Endotoxin (LAL) | Trial Production (100mL) | Structure Stability | ELISA | WB | IF | IHC | IP | SPR kinetics assay | Production | MSDS | Datasheet | Website | For sale
p-Tau 181 | 69 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 97.8 | 98.2 | >95 | >95 | 0-1 | 24.82 | OK | O | O | O | O | O | 3.11e-09 | O | O | O | O | O
P-Tau 181 | 77 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG2a | Kappa | E.coli | CHO-K1 | 97.3 | 98.2 | >95 | 98.16 | 0-1 | 23.52 | OK | O | O | O | O | O |  | O | O | O | O
P-Tau 217 | 97 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 96.5 | 97.1 | >95 | >95 | 0-1 | 54.3 | OK | O | O | O | O | O | 4.87e-09 | O | O | O | O | O
P-Tau 217 | 48 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 99.4 | 99.6 | >95 | >95 | 0-1 | 22.84 | OK | O | O | O | O | O |  | O | O | O | O
P-Tau 231 | 63 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 97.2 | 97.5 | >95 | >95 | 0-1 | 70 | OK | O | O | O | O | O | 9.87e-10 | O | O | O | O | O
P-Tau 231 | 1312 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 98.9 | 99 | >95 | >95 | 0-1 | 9.72 | OK | O | O | O | O | O |  | O | O | O | O
Neurofilament light polypeptide (NfL) | 1 | Leadgene | Closed | Done | Done | Done | Done | Done | Done | SP/CHO/E.coli | OK | 301-360 | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 100 | 100 | >95 | >95 | 0-1 | 17.78 | OK | O | O | O | O | O |  | O | O | O | O | O
Neurofilament light polypeptide (NfL) | 6 | Leadgene | Closed | Done | Done | Done | Done | Done | Done | SP/CHO/E.coli | OK | Check | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 99.1 | 99.2 | >95 | 99.2 | 0-1 | 7.83 | OK | O | O | O | O | O |  | O | O | O | O
Glial Fibrillary Acidic Protein (GFAP) | 21 | Leadgene | Closed | Done | Done | Done | Done | Done | Done | SP/CHO/E.coli | OK | 51-292 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 98.4 | 98.8 | >95 | 98.8 | 0-1 | 13 | OK | O | O | O | O | O |  | O | O | O | O | O
Glial Fibrillary Acidic Protein (GFAP) | 26 | Leadgene | Closed | Done | Done | Done | Done | Done | Done | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 95.3 | 95.5 | >95 | 95.5 | 0-1 | 26.73 | OK | O | O | O | O | O |  | O | O | O
Glial Fibrillary Acidic Protein (GFAP) | 19 | Leadgene | Colsed | Done | Done | Done | Done | Done | Done | SP/CHO/E.coli | OK | 51-292 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 99.2 | 99.4 | >95 | >95 | 0-1 | 10.2 | OK | O | O | O | O | O |  | O | O | O
Amyloid beta 42 | 211 | In house | Closed | Done | Done | Done | Done | Done | Done | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 95.2 | 98.8 | >95 | 98.8 | 0-1 | 10 | OK | O | O | O | O | O |  | O | O | O | O | O
註: SP =合成胜肽
優先
| 細胞株編號 | 委外代工 | 狀態 | 免疫注射 | 融合篩選 | 親和力測試 | 細胞擴增 | 抗體純化 | 全抗原親和力測試 | 抗原種類 | 抗原決定位確認 | 抗原決定位 | 結構穩定性測試 | 極限測試 | 交叉反應 | CDR 基因定序 | CDR定位/解序 | 抗體分型 | 輕鏈 | 基因轉殖 | 抗體表現 | 胺基 | 芳香族 | 還原態蛋白 | 非還原態蛋白 | 內毒素 | 生產量 | 結構穩定性測試 | 功能性驗證 |  |  |  |  | 親和力測試 | 產品生產 | 品質文件 |  | 上架 | 銷售
Monoclonal Ab | Clone No. | Oursource | Status | Immunization | Fusion/Selection | Affinity testing | Cell propagation | Ab purification | Antigen response | Antigens | Epitope mapping | Epitope region | Structure Stability | Limit of Detection | Cross-reactivity | CDR Sequencing | CDR mapping | Subtype of IgG | light chain | Vectoe Cloning | Ab expression | HPLC-SEC-214 | HPLC-SEC-280 | SDS-PAGE (Re) | SDS-PAGE (Non-R) | Endotoxin (LAL) | Trial Production (100mL) | Structure Stability | ELISA | WB | IF | IHC | IP | SPR kinetics assay | Production | MSDS | Datasheet | Website | For sale
pTau181 | 65 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa
pTau 181 | 3 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | Done | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 |  |  |  |  | 0-1 | Run out
pTau217 | 22 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG2b | Kappa
pTau 217 | 72 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | Done | Done | Done | Done | Done
pTau 217 | 123 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | Done | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 |  |  |  |  | 0-1 | Run out
pTau231 | 56 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG2a | Kappa
pTau 231 | 478 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | Done | Done | Done | Done | Done
pTau 231 | 311 | In house | Closed | Done | Done | Done | Done | Done | OK | SP | OK | NA | Done | Done | Done | Done | Done | IgG2a | Kappa | E.coli | CHO-K1 |  |  |  |  | 0-1 | Run out
Amyloid beta 40 | 213 | In house | Ongoing | Done | Done | Done | Done | Done | OK | SP | OK | 1-5 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | HEK293 | 98.6 | 98.7 | >95 | >95 | 0-1 | 3.45 | O | O | O |  |  |  | Ongoing |  | Done | Ongoing
Amyloid beta 42 | 24 | In house | Ongoing | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa
Amyloid beta 42 | 29 | In house | Ongoing | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa
Amyloid beta 40 | 33 | In house | Ongoing | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa
Amyloid beta 40 | 34 | In house | Ongoing | Done | Done | Done | Done | Done | OK | SP | OK | NA | OK | Done | Done | Done | Done | IgG1 | Kappa
SNCA | 2A10 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done |  |  | IgG2a | Kappa
SNCA | 3G2(M) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 95.2 | 96.1 | >95 | >95 | 0.1 | 41.18 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
SNCA | 4B10 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done |  |  | IgG1 | Kappa
SNCA | 5B12 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done |  |  | IgG1 | Kappa
SNCA | 5H8 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 98.6 | 98.7 | >95 | >95 | 0.1 | 10.09 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
SNCA | 6C6 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done |  |  | IgG1 | Kappa
SNCA | 9B5(M) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done | Done | Done | IgG2a | Kappa | E.coli | CHO-K1 | 95 | 95.1 | >95 | >95 | 0.1 | 54.05 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
SNCA | 11D11 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO | OK | 101-140 | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 1H5 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 96.2 | 97 | >95 | >95 | 0.1 | 20.76 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
S100B | 2A3 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 2C8 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | Checking | OK | 31-60 | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 2E1 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 2F11 (N) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-30 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 98.6 | 98.6 | >95 | >95 | 0.1 | 20.2 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
S100B | 4E2 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 98.8 | 98.9 | >95 | >95 | 0.1 | 20.22 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
S100B | 9F10 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 10D9 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | CHO | OK | Conformational | OK | Done | Done |  |  | IgG1 | Kappa
S100B | 4A10 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 31-60 | OK | Done | Done |  |  | Ongoing | Ongoing
S100B | 3B7 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-30 | OK | Done | Done |  |  | Ongoing | Ongoing
S100B | 8E8 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 31-60 | OK | Done | Done |  |  | Ongoing | Ongoing
TDP43 | 1E6 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2a | Kappa
TDP43 | 1F1 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 2A12 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 3A5 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 3E3(M) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 315-360 | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 97.9 | 98 | >95 | >95 | 0.1 | 42.15 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
TDP43 | 3G11 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 5A7 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done | Done | Done | IgG2b | Kappa | E.coli | CHO-K1 | 98.6 | 99.1 | >95 | >95 | 0.1 | 34.98 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
TDP43 | 6H2(M) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 315-360 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 10A9 | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 1-50 | OK | Done | Done |  |  | IgG2b | Kappa
TDP43 | 12F6(M) | E-Lab | Ongoing | Done | Done | Done | Done | Done | OK | SP/CHO/E.coli | OK | 361-412 | OK | Done | Done | Done | Done | IgG1 | Kappa | E.coli | CHO-K1 | 98.4 | 99 | >95 | >95 | 0.1 | 23.38 | O | O | O |  |  |  | Ongoing |  | Done | ongoing
pTau184 |  | In house | Pending | Done | Done | Done | Done
pTau235 |  | In house | Pending | Done | Done | Done | Done
pTau2-14 (Mouse) |  | In house | Pending | Done | Done | Done | Done | Done | OK (Polyclonal staue)
UCH-L1 |  | In house | Ongoing | Done | Done | Done | Done | Done | Ongoing
UCH-L1 N Terminus (54-74) |  | In house | Ongoing | Done | Done | Done | Done | Done | Ongoing
VHH-pTau217 |  | IREAL | Ongoing | Done | Ongoing
NfL (301-360) |  | In house | Ongoing | Ongoing
NfL (61-120) |  | In house | Ongoing | Ongoing
Amyloid beta 40 (28-40) |  | In house | Ongoing | Ongoing
Amyloid beta 42 (38-42) |  | In house | Ongoing | Ongoing
pTau3-15 |  | In house | Ongoing | Done | Ongoing
GFAP N/C fragment |  | In house | Preparing
Validation | Clone No. | Oursource | Status | Immunization | Fusion/Selection | Affinity testing | Cell propagation | Ab purification | Antigen response | 抗原種類 | Epitope mapping | Epitope region | Structure Stability | Limit of Detection | Cross-reactivity | CDR Sequencing | CDR mapping | Subtype of IgG | light chain | Vectoe Cloning | Ab expression | HPLC-SEC-214 | HPLC-SEC-280 | SDS-PAGE (Re) | SDS-PAGE (Non-R) | Endotoxin (LAL) | Trial Production (100mL) | Structure Stability | ELISA | WB | IF | IHC | IP |  | Production | MSDS Datasheet |  | Website | For sale
驗證中抗體 | 細胞株編號 | 委外代工 | 狀態 | 免疫注射 | 融合篩選 | 親和力測試 | 細胞擴增 | 抗體純化 | 全抗原親和力測試 | Antigens | 抗原決定位確認 | 抗原決定位 | 結構穩定性測試 | 極限測試 | 交叉反應 | CDR 基因定序 | CDR定位/解序 | 抗體分型 | 輕鏈 | 基因轉殖 | 抗體表現 | 胺基 | 芳香族 | 還原態蛋白 | 非還原態蛋白 | 內毒素 | 生產量 | 結構穩定性測試 | 功能性驗證 | [5 empty] | 產品生產 | 品質文件 |  | 上架 | 銷售
Porcine Reproductive and Respiratory Syndrome Virus (PRRSV) | 142 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine Reproductive and Respiratory Syndrome Virus (PRRSV) | 477 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine Reproductive and Respiratory Syndrome Virus (PRRSV) | 572 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine epidemic diarrhea virus (PEDV) | 168 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine epidemic diarrhea virus (PEDV) | 170 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine epidemic diarrhea virus (PEDV) | 203 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Porcine epidemic diarrhea virus (PEDV) | 233 | In house | Closed | Done | Done | Done | Done | Done | OK | Inactivated viral lysate | NA |  | Done | Done | Done | Done | Done
Norovirus | 45 | In house | Closed | Done | Done | Done | Done | Done | OK | Recombinant protein | NA |  | Done | Done | Done | Done | Done

## Antigen
Project | Lot | Protein (CHO) | Volume | (mg/ml) | Amount (mg) | SDS-PAGE (Reducing) | SDS-PAGE (Non-Reducing) | Endotoxin level (EU/mg) | MW kDa | Buffer
9PF0SM001 | H-202405250528 | protein S100-B | 100ml | 0.72 | 2.7 | <50% | <50% | <1 | 12kDa(12kDa) | PBS
9PF2QS001 | W-202406230084 | Alpha-synuclein | 100ml | 2.15 | 10.5 | >95% | >97% | <1 | 16kDa(16kDa) | PBS
9PF0SM003 | H-202405250528 | TAR DNA-binding protein 43 | 100ml | 0.54 | 2.32 | >65% | >65% | <1 | 46kDa(46kDa) | PBS
9PF12X001 | M-202405190707 | Tau | 100ml | 1.525 | 8.24 | <50% | <50% | <1 | 48kDa(48kDa) | PBS
9PF12X002 | M-202405281069 | NfL | 100ml | 0.2825 | 1.44 | >65% | >65% | <1 | 63kDa(63kDa) | PBS
9PF12X003 | M-202405190729 | GFAP | 100ml | 0.569 | 3.19 | >65% | >65% | <1 | 52kDa(52kDa) | PBS
Project | Lot | Protein (E.coli) | Volume | (mg/ml) | Amount (mg) | SDS-PAGE (Re) | SDS-PAGE (Non-Redu) | Endotoxin level (EU/mg) | MW kDa
9PF12Y001 | 20240610F004 | Tau | 1L | 0.43 | 3.87 | >85 | >85 | <50 | 47kDa(47kDa) | PBS
9PF7XT001 | P-202409040786 | Tau | 1L | 0.195 | 3.4 | >95 | >95 | <100 | 47kDa(47kDa) | 20mM Hepes +150mM NaCl, pH7.5
9PF7XT001 | P-202409040787 | Tau | 1L | 0.35 | 6.3 | >95 | >95 | <50 | 47kDa(47kDa) | 20mM PB +300mM NaCl, pH7.4
9PF453001 | 20240814F001 | NfL | 1L | 1.29 | 7.22 | >85 | >85 | <5 | 63kDa(63kDa) | 15mM Tris,85mM Glycine pH8.5,2mM DTT
9PF7P6001 | P-202409131584 | GFAP | 1L | 1 | 35 | >95 | >95 | <1 | 51kDa(51kDa) | 15mM Tris+85mM Glycine, pH8.5 + 2mM DTT
9PF47K001 | 20240802F002 | GSK-3 beta | 1L | 0.88 | 7.92 | >65 | >65 | <1 | 48kDa(48kDa) | 100mM Na2CO3-NaHCO3 pH10.0+2mM DTT
9PF2QS001 | 9PF0SM002 | Alpha-synuclein | 1L | 2.235 | 6.71 | >95 | >95 | <1 | 16kDa(16kDa) | PBS,pH7.2-7.4
9PFN2X001 | W-202412050637 | protein S100-B | 1L | 0.35 | 16.18 | >85 | >85 | <1 | 12kDa(12kDa) | 1xPBS,10%glycerol
9PFF5Y002 | P-202412190910 | TAR DNA-binding protein 43 | 1L | 0.15 | 1.02 | >65 | >65 | <50 | 46kDa(46kDa) | 50 mM Tris-HCl +150 mM NaCl +10%trehalose pH 8.0
9PFXTH001 | P-202504040046 | UCH-L1 | 1L | 0.5 | 95.6 | >95 | >90 | <5 | 26kDa(26kDa) | PBS+300mM Nacl+5%Trehalose+10%Glycerin pH7.4

## LFA
LFA | ng/mL | ppb | 委託商 | 報告 | 討論
Tetracycline | 25 | 25 | 偉喬 | R1121004003 | Pending
Ampicillin | 4 | 4 | 偉喬 | R1121018001 | Pending
cephalexin | 3-5 | 3-5 | 偉喬 | R1121018002 | Pending
LFA | Titer dilution |  | 委託商 | 報告 | 討論
PRRSV virus | 64 |  | 偉喬 | R1130217002 | Pending
PEDV Virus | 64 |  | 偉喬 | R1130217001 | Pending
mg/L（ppm）
ug/L（ppb）
ug/mL（ppm）
ng/mL（ppb）
pg/mL（ppt）

## GFET
GFET testing (Laser induced Graphene)
Target | Antibody | Antigen | LoD | Status | Notes
Aβ42 | Nexbiotek | Nexbiotek | 10 fg/mL | Final | Data inquired
pTau 217 | Nexbiotek | Nexbiotek | 100 fg/mL | Recheck | Data inquired
pTau 217/Aβ42 | Nexbiotek | Nexbiotek |  | Ongoing
Aβ40 | Nexbiotek | Nexbiotek |  | Wait for Ab